## March
Abraham Design
Project timelines for client: Xfai
MARCH | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
PROJECT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
XFAI.com
CSS cleanup
[7 empty] | Aesthetic tweaks (front-end dev) |  |  |  |  | Changes
Promo video: New Potentializer (3min)
Keyframes
Voice recording
|  |  | Video animation |  |  | Changes
Music
Promo video: Gas Fee (1min)
Script
[8 empty] | Storyboard |  | Changes
[11 empty] | Illustrations |  |  | Changes
[15 empty] | Animations |  |  |  |  | Changes
Voice recording
Promo video: TBD (1min)
Script
[18 empty] | Storyboard |  | Changes
[21 empty] | Illustrations |  |  | Changes
[25 empty] | Animations |  |  |  |  | Changes
Voice recording
Dashboard (Phase 1, 2 and 3)
[7 empty] | Wireframes | [6 empty] | Changes
[16 empty] | Visual designs |  |  |  | Changes
[22 empty] | Front end dev |  |  |  |  | Changes
KYC integration
[16 empty] | Visual des. | Changes
Front end d.
Promo video: 1:30 from a template
[7 empty] | Storyboard |  | Changes
[10 empty] | Animations |  |  | Changes